## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Login @xiyuanzhou | 1 | 5 | 1 | 4 | 100% | bar: PERIODS 1 to PERIODS 2; PERIODS 5 to PERIODS 7
Logout @xiyuanzhou | 1 | 6 | 1 | 6 | 100% | bar: PERIODS 1 to PERIODS 2; PERIODS 7
Create Account @xiyuanzhou | 2 | 4 | 2 | 5 | 100% | bar: PERIODS 1 to PERIODS 2; PERIODS 6 to PERIODS 7
Delete Accounts @xiyuanzhou | 4 | 8 | 4 | 6 | 100% | bar: PERIODS 1 to PERIODS 3; PERIODS 5 to PERIODS 12
Search Items @ahmetmutlugun | 4 | 2 | 4 | 8 | 100% | bar: PERIODS 4 to PERIODS 12
Post Items @seafu47 | 4 | 3 | 4 | 6 | 100% | bar: PERIODS 6 to PERIODS 9
Delete Items @seafu47 | 5 | 4 | 5 | 3 | 100%
Purchase Item @seafu47 | 5 | 2 | 5 | 5 | 100% | bar: PERIODS 7 to PERIODS 9
User Profile @RommelAquinoJr | 5 | 2 | 5 | 6 | 100% | bar: PERIODS 3 to PERIODS 4; PERIODS 7 to PERIODS 12
Translation @RommelAquinoJr | 6 | 5 | 6 | 7 | 100% | bar: PERIODS 6 to PERIODS 14
Add pictures @ahmetmutlugun | 6 | 1 | 5 | 8 | 100% | bar: PERIODS 4 to PERIODS 5; PERIODS 7; PERIODS 9 to PERIODS 12; PERIODS 14
Sorting @seafu47 | 9 | 3 | 9 | 3 | 100% | bar: PERIODS 9 to PERIODS 14
Chinese @seafu47 | 9 | 6 | 9 | 7 | 100% | bar: PERIODS 9 to PERIODS 14
Turkish @ahmetmutlugun | 9 | 3 | 9 | 1 | 100% | bar: PERIODS 9 to PERIODS 14
Dark Mode @ahmetmutlugun | 9 | 4 | 8 | 5 | 100% | bar: PERIODS 3 to PERIODS 14
Smooth Interface @everyone | 10 | 5 | 10 | 3 | 100% | bar: PERIODS 3 to PERIODS 14